# New Risk analysis

Table 2 - A risk analysis table
Risk	Probability	Impact	Combined Risk	Mitigation Plan	Contingency Plan
Unrealistic time plan and poor time management.	High	High	High	Create work schedule and stick to it.	If I am unable to stick to my work schedule, I must adapt my approach to work and create an undated, more realistic schedule.
Coronavirus affects me or a close family member, negatively effecting my work.	Medium	High	High	Stay safe during the quarantine to keep everyone safe and mitigate any risks of me catching anything.	Inform the University as soon as a situation develops so we can arrange something.
Coronavirus has a greater impact on Swansea University and effects the available support and deadlines.	Medium	High	Medium	Keep informed with the University College of Science and supervisor to any news effecting the University.	Keep my options open? Keep updated?
No correlation between attention and mouse tracking data can be found.	Low	High	Medium	Attempt as many different methods of classification early before writing in depth about them.	If no insights can be gained from the given dataset, I will attempt to find correlations in other datasets.

Risks:
- BIGGEST we find that there is no correlation between attendtion and mouse data and nothing is prooved.
- COID19 effecting the UK more. - I was considering running more lab studies to get more data but the shutdown has stopped that ambishion.
    It has already effected, anything worse like close family and elderly parents getting ill so supervisor or me would be a risk.
    Plan ahead, wash hands.

Tabel 2 - A risk analysis table
Risk	Probability	Impact	Combined Risk	Mitigation Plan	Contingency Plan
Unrealistic time plan and poor time management	High	High	High	Create work schedule and stick to it.	If I am unable to stick to my work schedule I must adapt my approach to work and create an undated, more realistic schedule.
Developing a product for the wrong target audience	Medium	Medium	Medium	Research into what current GCSE pupils learn and plan my product around that.	If the product isn’t helpful to GCSE pupils then I will use it to teach other pupils computer science e.g. college night class.
Unusable resources	Medium	Medium	Medium	Ensure that my research into existing teaching methods is extensive enough so that teachers are able to use them.	If my resources are unusable for teaching then I will have to repurpose them as demonstrations of swarm robots behaviour.
Permanent change of teaching requirements	Low	Medium	Low	Ensure that my background research is accurate and up to date so that any change would not be a surprise.	In this case I will have to then change the target audience for my project. It may not be useful to WJEC students but it may still be useful to others, such as those who would like to learn about swarm robotics in their own time, or just to showcase swarm robotic algorithms
Technical challenge can't overcome	Low	Low	Low	I will consult the Greenfoot API for details about how the classes work, and read documentation about swarm robotics algorithms.	If I am unable to overcome a technical challenge I must then change which algorithms I wish to showcase.

## Expanded Risks
Unrealistic time plan and poor time management:
This is perhaps the biggest risk when attempting a project of this scope. If I fail to create a realistic plan, or fail to stick to that plan then there is a risk of the project and all related aspects not being completed on time and to a good standard. To prevent this risk I have been thorough when creating my work schedule. Additionally a Gantt chart has been created to help me with time management. If I am also able to stick to this schedule then this risk should not be too insurmountable. This would affect all stages of development but particularly the deadlines such as the Gregynog event, project fair, and project dissertation.

Developing a product for the wrong target audience
Another prevalent risk with my project is that the end product is pitched at the wrong level and does not satisfy the project aims. Aim D is “To create resources related to my project that can be used to teach WJEC computer students.” This aim might prove challenging as WJEC GCSE student have a strict specification, it is a concerning risk that the project and resources that I create will be either too advanced, to elementary, or irrelevant to GCSE students. My project will fail to meet the required aims if this risk prevails. Though the aims will not be met the project will not be useless as it can still be used by alternative groups e.g. Key Stage 3 if the resources are too elementary or AS Level if the resources are too advanced.

Unusable resources
Due to my lack of teaching experience there is a risk that the teaching resources that I create for computer science and swarm robotics may be unsuitable for their purpose. It may be the case that the tasks and programs I design may be unusable in a classroom setting or unclear when explaining concepts and ideas to people new to the field of computers. The high combined risk shows the severity of this risk therefore I will do research on what teaching tools and resources already exist both online and in the classroom so that I can cater my project into being similar to them.

Permanent change of teaching requirements
If the WJEC was to change the specification in the middle of completion of the project, or shortly afterwards, then the projects usability would be at risk. Although the project would not be suitable for the target audience, it would still showcase the concept of swarm robotics. The teaching resources could be repurposed to cater for other groups with an interest in learning swarm robotics. This rick could come into fruition at anypoint in the development of my project so I must be vigilant in being up to date about the WJEC specifications.

Technical challenge can't overcome
There is a risk that I encounter problems with Greenfoot that I am unable to overcome. I am creating resources and scenarios about robotics in Greenfoot because no such resources already exist. This means that if I have difficulties bringing these algorithms to life then there is no existing work that I can use as guidance in this specific environment. This would occur towards the beginning of the project when I am first implementing the algorithms into Greenfoot.

tasks